## Sheet1
Leverett Trails Committee
7:30 p.m. January 23, 2017 Town Hall, 9 Montague Rd, Leverett, MA 01054
Members Present: | Rocky Adriance, Miho Connolly, Joan Godsey, Marcia Jackson, David Powicki, Adam Wellen, Mary Alice Wilson, Martin Wobst
| Status | Plans | Person(s) Responsible | Notes
STATUS OF TRAILS
Bill Rivers | 1. Railing needs to be installed on second bridge. 2. Old metal bridges need to be removed from the property. 3. 2 logs down across trails which could be removed but are not hard to get over. New laminated maps have gone up. | Railings will be installed on next workday. The highway department expressed an interest in the metal bridges. | Miho will get in touch with the Hwy Dept about the metal bridges. WORK DAY 3/25@8:30AM to install railings.
Friendship Trail | Small foot bridge collapsing; two walkway planks could be replaced.
4H Forest | Neal's new trail is wonderful. It still needs some finishing up, but can be blazed and opened to the public. | We will blaze Neal's trail with yellow. The bench at the 4-H parking lot should be moved to the poetry box at Woodard's Corner. | David will install blazes. Mary Alice will make a GPS track for maps. David will move the bench.
Gordon King | We have a pile of brush to burn. Joe Sincuk has advised us that weeds around the blueberry bushes should be kept down in order to decrease competition. | The opening day for the library exhibit about Gordon and Frances King is April 1. We would like to incorporate stewardship of his property to the proceedings. | WORKDAY 4/1 @ 8:30AM
Teawaddle Hill Farm | Western loop of trails in NE corner of property are not blazed, but obvious. | They are marked on the map but will remain unblazed.
OTHER BUSINESS
Gordon & Frances King Library Exhibit | Brooke Thomas has suggested that we use the April exhibit time at the Library’s community room to celebrate the lives of Gordon and Frances King. The opening event at 1:00PM on April 1st will include photographs, videos, and stories about the pair. To be co-sponsored by Rattlesnake Gutter Trust, Leverett Trails Committee, Leverett Historical Society, and Conservation Commission (TBD). | LTC supports the exhibit. We will hold a work day at the Gordon King Life Estate on April 1 before the opening event. | If you have any materials or stories that we can scan and use in the exhibit or event or if you would like to help in the planning, please contact Mary Alice Wilson at maryalice1936@gmail.com or Brooke Thomas at rbthomas@anthro.umass.edu. | This exhibit could become a template for future library exhibits that honor influential Leverett citizens.
Bill Rivers CA "Hike-a-thon" | Sarah Marcus contacted the LTC about coordinating a "hike-a-thon" in the Bill Rivers trails behind the LES. | The LTC is interested in and supports this plan. Perhaps students could help clear a new trail in the Bill Rivers property? We will need to find and map out a trail. | Sarah and a small group will explore options for new trails.
Cave Hill Geology & Nature Walk April 29 | Nancy Goodman and Richard Little are leading a walk at Cave Hill through PVI & GCC. They are expecting ~35 cars. | Roadsides around Cave Hill CA may be congested at this time.
DATES
| Saturday, Feb 11 8:30AM - 12:30PM (Rain date: Saturday, Feb 25) | Bill Rivers CA: Reconnaissance/bushwhacking to map out a new trail for students to work on at the proposed LES "hike-a-thon" | Attendees limited to those at meeting and those invited by word of mouth.
WORK DAYS | Saturday, March 25 8:30AM - 12:30PM | Bill Rivers CA: Construction of railings on existing bridges. Removal of fallen logs (chainsaws)?
| Saturday, April 1 8:30AM - 12:30PM | Gordon King Life Estate: Weeding, clean-up, brush burning.
OTHER EVENTS IN TOWN | Widening the Circle: Making the Great Outdoors Accessible | Lucy Gertz and Macy Marchello provide an award-winning workshop on how to make trails accessible to all persons. $25; pre-registration required. (See flier) | Tues, Jan 31 1:00 - 5:00pm @ Hitchcock Center
NEXT MEETING: | 7:30p.m. February 27, 2017 | The third Monday of February (2/20) is Presidents' Day.