## Sheet1
Leverett Trails Committee
7:30 p.m. February 27, 2017 Town Hall, 9 Montague Rd, Leverett, MA 01054
Members Present: | Rocky Adriance, Jeff Blanchard, Laurie Brown, Miho Connolly, Joan Godsey, Neal Erickson, Marcia Jackson, Adam Wellen, Mary Alice Wilson, Martin Wobst
| Status | Plans | Person(s) Responsible | Notes
STATUS OF TRAILS
Bill Rivers | 1. Railing needs to be installed on second bridge. 2. Old metal bridges need to be removed from the property. 3. 2 logs down across trails which could be removed but are not hard to get over. More accurate maps have gone up. | Railings will be installed on next workday. Could get help from chainsaw crew to clean up logs. The highway department expressed an interest in the metal bridges. | Miho will continue to reach out to the Hwy Dept about the metal bridges. WORK DAY 3/25@8:30AM to install railings.
4H Forest | Neal's new trail ("South Overlook") has been blazed with yellow and is marked on new E Leverett trails maps. There is also a tree down on the 4-H Vernal Pool trail | We want to figure out a way to access the island. A log needs to be sawed. Trail markers may need to be moved around. | BRAINSTORM ways to get to the island. Chainsawyer to remove log on South Overlook trail, Vernal Pool Trail | Please walk this new trail, enjoy the beautiful scenery, and bring forward any other possible kinks/improvements!
Gordon King | Some red cedars are hung up over the trail at Woodard's Corner. There is an old fence behind the beaver pond that could be removed. | The opening day for the library exhibit about Gordon and Frances King is April 1. In the morning, we will weed around the bushes, remove the fencing behind the beaver pond, remove hung up and fallen trees, and burn the brush pile. | WORKDAY 4/1 @ 8:30AM. Chainsawyers will remove hung up and fallen logs. | We could offer guided trail walks at the dedication in the afternoon
Ed Field Trail | The change in signage from orange blazes to white posts is confusing. The sign posts keep falling, and more posts are needed. | We should include a sign that indicates the change in signage, and should also mark the posts with the corresponding color. | Mary Alice will drop off posts at the ConCom office; anyone can add them to the trail as necessary. Volunteer to mark posts?
Teawaddle Hill Farm | There is interest in creating trails in the western area of the property |  | Mary Alice will talk to Gwyn about the possibility of putting in new trails
OTHER BUSINESS
Mapboard Inventory | Mary Alice has completed an inventory of existing mapboards on our trails! Inventoried mapboards have updated maps. |  | Let Mary Alice know if you find any outdated maps on the trails!
Eversource "Rte 66" | Members expressed discontent at the creation of thoroughfares in the Eversource right-of-ways | Is it possible to stop National Grid from undertaking a similar project? | Miho will discuss the issue with DEP
Gordon & Frances King Library Exhibit | The April library exhibit will celebrate the lives of Gordon and Frances King. The opening event at 1:00PM on April 1st will include photographs, videos, and stories about the pair. Co-sponsored by Rattlesnake Gutter Trust, Leverett Trails Committee, Leverett Historical Society, and Conservation Commission. | LTC supports the exhibit. We will hold a work day at the Gordon King Life Estate on April 1 before the opening event. | If you have any materials or stories that we can scan and use in the exhibit or event or if you would like to help in the planning, please contact Mary Alice Wilson at maryalice1936@gmail.com or Brooke Thomas at rbthomas@anthro.umass.edu. | This exhibit could become a template for future library exhibits that honor influential Leverett citizens.
Bill Rivers CA "Hike-a-thon" | Sarah Marcus contacted the LTC about coordinating a "hike-a-thon" in the Bill Rivers trails behind the LES. A small group marked a few new trails that head into the back of the property. | Yellow stream loop should be de-flagged in consideration of cultural structures. Trail paths should probably be tweaked. Return loop needs to be mapped. Perhaps we could fell some trees to create a vista at the top of the hill. A bench should be placed at the top of the hill. | Please walk the trails and adjust flags for ease of walking. Miho will look into the deed to investigate rules on tree cutting. | We are waiting for word from Sarah and LES before we proceed with this project. Students could name the trail or hill? We could keep a notebook of wildlife sightings?
Community Preservation Act Grant | The public hearing for the Trails Improvement grant application will be on March 1 at 7:30pm at the Town Hall. |  | Miho, David
Cave Hill Geology & Nature Walk April 29 | Nancy Goodman and Richard Little are leading a walk at Cave Hill through PVI & GCC. They are expecting ~35 cars. | Roadsides around Cave Hill CA may be congested at this time.
DATES
| Saturday, Feb 11 8:30AM - 12:30PM (Rain date: Saturday, Feb 25) | Bill Rivers CA: Reconnaissance/bushwhacking to map out a new trail for students to work on at the proposed LES "hike-a-thon" | Attendees limited to those at meeting and those invited by word of mouth.
WORK DAYS | Saturday, March 25 8:30AM - 12:30PM | Bill Rivers CA: Construction of railings on existing bridges. Removal of fallen logs (chainsaws)?
| Saturday, April 1 8:30AM - 12:30PM | Gordon King Life Estate: Weeding, clean-up, brush burning.
OTHER EVENTS IN TOWN
NEXT MEETING: | 7:30p.m. March 20, 2017