## Sheet1
Leverett Trails Committee
7:30 p.m. April 17, 2017 Town Hall, 9 Montague Rd, Leverett, MA 01054
Members Present: | Rocky Adriance, Laurie Brown, Miho Connolly, Neal Erickson, Joan Godsey, Martin Wobst
| Status | Plans | Person(s) Responsible | Notes
STATUS OF TRAILS
Bill Rivers | 1. Old metal bridges need to be removed from the property. 2 Some logs and overhung snags that could be removed. 3. More bog bridges could be installed by stone structures. 4. More signage would be useful on the red trail. |  | Joan will ask Ananda at the Transfer Station about taking the metal bridges.
4H Forest | Neal's trail needs more benching, and signage by the powerlines. | Put in 1 or 2 benches. Brainstorm ways to access the island. Some trail markers may need to be revised. Vista pruning of dead branches? | WORKDAY 5/6 @ 8:30AM
Gordon King | Approximately 2/3 of the bushes were pruned at the April 8 workday, and more irrigation tubing was pulled. The brush pile was not burned. | Joe Sincuk is interested in professionally managing the blueberry bushes, including pesticide applications and bird netting. We should brainstorm funding sources for this project.
Ed Field Trail | We can nail green trail tags to the white posts on the Vernal Pool trail so that it is easier to follow. | We need to consolidate a color for the VP trail. More stakes should be acquired and put in-- perhaps garden stakes? | Miho
Teawaddle Hill Farm | There is a gap in the bog bridges on the red trail that really needs to be filled. | We need 3~4 bog bridges here. | Workday TBD
Cave Hill | Neal has cleared out an alternative route for the blue trail on Town land to avoid a wet patch. A bog bridge would be useful at the stream crossing on the Town Farm Loop. | Change blazes on blue trail and remove fallen log (chainsaw). Boundary Rocks trail spur will be closed and blazes removed. | Miho
East Leverett Meadow | Rocky has fixed ruts and reinstalled the mailbox with trail maps. The sign at the entrance has been changed by an unknown party. | Perhaps a strip could be mown through the middle of the property for the winter to avoid the path through the wet area on the northeast side.
OTHER BUSINESS
Eversource "Rte 66" | Members expressed discontent at the creation of thoroughfares in the Eversource right-of-ways | Is it possible to stop National Grid from undertaking a similar project? | Miho will discuss the issue with DEP | The roads are required by state? feds? to ensure faster repairs in storms.
The Kings of Leverett Library Exhibit | The work day and dedication event on April 8 were well attended and successful. | The April library exhibit will celebrate the lives of Gordon and Frances King. The opening event at 1:00PM on April 22 will include photographs, videos, and stories about the pair. | Co-sponsored by Rattlesnake Gutter Trust, Leverett Trails Committee, Leverett Historical Society, and Conservation Commission.
LES Leverett Trails Appreciation Day | Has been postponed; likely until the fall.
Community Preservation Act Grant | The trails grant application has been approved by the CPC to be voted on at Town Meeting. |  | Please join us at Town Meeting to support our proposal!
Cave Hill Geology & Nature Walk April 29 | Nancy Goodman and Richard Little are leading a walk at Cave Hill through PVI & GCC. They are expecting ~35 cars. | Participants will be allowed to park at the Peace Pagoda.
DATES
| Saturday, Feb 11 8:30AM - 12:30PM (Rain date: Saturday, Feb 25) | Bill Rivers CA: Reconnaissance/bushwhacking to map out a new trail for students to work on at the proposed LES "hike-a-thon" | Attendees limited to those at meeting and those invited by word of mouth.
WORK DAY | Saturday, May 6, 8:30AM @ 4-H Property | Finishing up the yellow trail-- vista pruning, installing benches, leveling the steep area.
OTHER EVENTS IN TOWN
NEXT MEETING: | 7:30p.m. May 15, 2017